## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Restaurant menu and ordering system | Fatema karout | 2020-07-06 | 2020-10-05 |  | 35% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| log in |  | Fatema |  | 2022-09-03 | 2022-09-13 | 10 | completed
| Add acount |  | Yesra |  | 2022-09-03 | 2022-09-07 | 4 | completed
| enter password |  | Fatema |  | 2022-09-07 | 2022-09-12 | 5 | completed
Feature 3
| Reservation table |  | Yesra |  | 2022-09-09 | 2022-09-13 | 8 | inprogess
| Activate table |  | fatema |  | 2022-09-16 | 2022-09-24 | 1 | inprogess
| Deactivate table |  | Yesra |  | 2022-09-17 | 2022-09-17 | 4 | not started
| Accept order |  | fatema |  | 2022-09-25 | 2022-10-05 | 10 | notstarted
| Add items in order to customer's meal |  | Yesra |  | 2022-09-25 | 2022-09-29 | 4 | notstarted
Feature 8

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.